## Sheet1
ID | TASK DESCRIPTION | DURATION | START DATE | FINISH DATE | Team Member | NOTES
1 | Timebox 1
1.1 | Initial Client Meeting | 30 mins | 2023-10-19 | 2023-10-19 | All Team Members
1.2 | Define Project Objectives, scope, and key deliverables | 30 mins | 2023-10-19 | 2023-10-19 | All Team Members
1.3 | Establish Project Plan
2 | Timebox 2
2.1 | Task 1
2.2 | Research and analyze various system architectures | 1 hour | 28/11/2023 | 28/11/2023 | Mujeeb
2.3 | Create Risk Asessment | 1 hour | 28/11/2023 | 28/11/2023 | Liam
3 | Timebox 3
3.1 | Define user stories and use cases to form how system operates
3.2 | Develop strategic BPMN models that capture the system architecture | 2 hours | 2023-01-12 | 2023-02-12
4 | Timebox 4
4.1 | Review BPMN models and i* models with supervisor | 30 mins | 2023-05-12 | 2023-05-12 | All Team Members
4.2 | Refine i* diagram based on feedback | 2 hours | 2023-05-12 | 2023-05-12 | Liam
5 | Timebox 5
5.1 | Finalize Report
5.2 | Get client approval
5.3 | Create presentation
5.4 | Create presentation slides
6 | Timebox 6
6.1 | Meet with client for any changes
6.2 | implement changes
6.3 | get client approval on changes
7 | Timebox 7
7.1 | Create BPMN model for effcientcy
7.2 | Review models and make addjustments based on feedback
8 | Timebox 8
8.1 | Analyis project for any automation potential
8.2 | Implement changes
9 | Timebox 9
9.1 | Design UI
9.2 | Review UI
9.3 | Implement changes