## Sheet1
Risk | Impact Level | Probability Level | Mitigation Plan
Lose communication with client contact | 7 | 2 | suspend hand over untill communication resumes.
Project scope alterations affecting deliverable timelines | 6 | 4 | Before Development define requirements with client signed off
Poor project communication | 9 | 3 | Have regular meetings within the team to keep every member up to date with that is being done and what they have to do.
Budget Constrants, unexpected costs or budget constraints may arise during the project timeline. | 7 | 1 | conduct a budget analysis at beginning of the project and identify any potential areas of cost overruns.
Hardware Incompatibility | 9 | 3 | Have clear software and hardware requirements to ensure smooth handover on completion.